## 17.09.2018
No. of Actions as at 17/09/2018
|  |  |  | Not Started | 24 | 40% - 69% | 19
|  |  |  | N/A | 3 | 70% - 99% | 23
|  |  |  | 1% - 39% | 17 | 100% | 12
| Vision | Objective | Action |  | Priority | By Whom | Timescale | % Complete | Comments
1.01 | A HEALTHIER | Physically Active | Sports |  | 1 | Skipness Village Hall | 1-2 yrs | 20% | 23/08/2018 2018 Community Benefit to support
| COMMUNITY |  | Encourage sports in Skipness Hall. |  |  | Committee |  |  | upgrading Skipness Village Hall.
1.02 | A HEALTHIER | Physically Active | Walks/Cycle Routes/Sports |  | 2 | TSCC | 6-12 mths | 20% | 23/08/2018 Sustrans currently looking at a 2-3 year lead in
| COMMUNITY |  | New path to West Loch to complete |  |  | Transport Scotland |  |  | lead in time for a cycle/pedestrian route from Tarbert
|  |  | 6 mile circular walk from village |  |  | West Loch Shores |  |  | to Kennacraig.
centre via West Loch and Corranbuie
track.
1.03 | A HEALTHIER | Physically Active | Walks/Cycle Routes/Sports |  | 1 | TSCT | Current and | 45% | 23/08/2018 White Shore path has been upgraded.
| COMMUNITY |  | Improve and maintain existing |  |  | Paths for All | ongoing |  | Castle paths have been completed.
|  |  | footpath network. |  |  | ABC
1.04 | A HEALTHIER | Physically Active | Walks/Cycle Routes/Sports |  | 1 | TSCT | Achieved and | 90%
| COMMUNITY |  | Restore White Shore track. |  |  |  | ongoing
1.05 | A HEALTHIER | Physically Active | Walks/Cycle Routes/Sports |  | 4 | Kintyre Way New Co | 2 yrs | N/A | 23/08/2018 Awaiting redevelopment of Kintyre Way.
| COMMUNITY |  | Link Kintyre Way to Ardrishaig.
1.06 | A HEALTHIER | Physically Active | Walks/Cycle Routes/Sports |  | 4 | TSCC |  | Not Started
| COMMUNITY |  | Increase all ability section in walks. |  |  | ABC
Kintyre Way New Co
1.07 | A HEALTHIER | Physically Active | Walks/Cycle Routes/Sports |  | 4 | TSCC | 2 yrs | 20% | 23/08/2018 Sustrans currently looking at a 2-3 year
| COMMUNITY |  | Link Kintyre Way and cycling routes. |  |  | Sustrans |  |  | lead in time for a cycle/pedestrian route from Tarbert
to Kennacraig.
1.08 | A HEALTHIER | Physically Active | Walks/Cycle Routes/Sports |  | 3 | TSCC | 4 yrs | 20% | 23/08/2018 Sustrans currently looking at a 2-3 year
| COMMUNITY |  | Cycle track to Kennacraig. |  |  | Sustrans |  |  | lead in time for a cycle/pedestrian route from Tarbert
[6 empty] | Transport Scotland |  |  | to Kennacraig.
1.09 | A HEALTHIER | Physically Active | Walks/Cycle Routes/Sports |  | 1 | TSCT | Ongoing | 45% | 23/08/2018 Community Benefit procedures in place
| COMMUNITY |  | Support sports groups with funding, | [5 empty] | and 2017-18 grants dispersed.
governance and safeguarding.
1.10 | A HEALTHIER | Physically Active | Housing |  | 2 | Alienergy | Ongoing
| COMMUNITY |  | Tackle dampness and poor |  |  | ACHA
|  |  | insulation of housing. |  |  | Fyne Homes
2.01 | A HEALTHIER | Social Involvement | Social Involvement |  | 3 | All | Ongoing | 80% | 23/08/2018 Events promoted through social media
| COMMUNITY |  | Promote local community groups' | [5 empty] | and local advertising.
activities, events and achievements as
well as provide information on how to get involved via diary.
get involved via diary.
2.02 | A HEALTHIER | Social Involvement | Social Involvement |  | 2 | TSCT | 6 mths from | 20% | 23/08/2018 Feasibility study required to be carried
| COMMUNITY |  | Review use of school minibus. |  |  | Schools | study |  | out.
Sports groups
2.03 | A HEALTHIER | Social Involvement | Social Involvement |  | 2 | TSCT | 1 yr | 20% | 23/08/2018 Trust membership up 30% by end of
| COMMUNITY |  | Campaign to recruit new Trust | [5 empty] | March 2018.
membership.
2.04 | A HEALTHIER | Social Involvement | Social Involvement |  | 1 | TSCT | Ongoing | Not Started
| COMMUNITY |  | Review, improve and promote a central |  |  | TEC
|  |  | single community notice board both |  |  | TSCC
|  |  | physically in the village centres and |  |  | ABC
online and incorporate into new
visitor project.
2.05 | A HEALTHIER | Social Involvement | Social Involvement |  | 1 | TSCC | Ongoing | Not Started
| COMMUNITY |  | Co-ordinate events and activities via a |  |  | TEC
diary system to ensure limited overlap
of activities and maximum potential
for attendance/participation.
2.06 | A HEALTHIER | Social Involvement | Social Involvement |  | 4 | 3rd Sector Interface | 2 yrs | 20% | 23/08/2018 Stalled.
| COMMUNITY |  | Men's and women's sheds.
2.07 | A HEALTHIER | Social Involvement | Social Involvement |  | 2 | TSCT | Achieved | 100% | 23/08/2018 Community Benefit Fund.
| COMMUNITY |  | Support existing community places to |  |  | TVH
|  |  | maintain and improve facilities. |  |  | TALC
THA
3.01 | A HEALTHIER | Space for Relaxation, | Spaces for Relaxation, Contemplation |  | 2 | TSCT | Achieved | 100% | 23/08/2018 Annual clean of White Shore.
| COMMUNITY | Contemplation and | and Reflection |  |  | TSCC | and ongoing
|  | Reflection | Re-instate community cleaning of |  |  | LFYC
|  |  | beaches. |  |  | THA
3.02 | A HEALTHIER | Space for Relaxation, | Spaces for Relaxation, Contemplation |  | 2 | TSCT | Achieved | 70% | 23/08/2018 Orchard, community woodland, castle
| COMMUNITY | Contemplation and | and Reflection |  |  | TSCC | and ongoing |  | and White Shore path.
|  | Reflection | Identify areas within villages that need |  |  | Tarbert Academy
|  |  | clearing and cleaning. |  |  | ABC
4.01 | A HEALTHIER | Well Nourished | Nutrition |  | 3 | NHS | Ongoing | 45% | 23/08/2018 Work through school with food bank to
| COMMUNITY |  | Promote the use of fresh foods and |  |  | Retailers |  |  | create recipe cards. After School care cooking
|  |  | healthy diets. | [5 empty] | lessons with children.
4.02 | A HEALTHIER | Well Nourished | Water Supply |  | 2 | Scottish Water | 2 yrs | Not Started
| COMMUNITY |  | Investigate water quality and supply
issues to Skipness and Claonaig.
5.01 | A HEALTHIER | Access to Good Health | Care Services |  | 1 | TSCC | Ongoing | 100%
| COMMUNITY | Care Services | Maintain current provision of health |  |  | NHS
|  |  | care. |  |  | ABC
5.02 | A HEALTHIER | Access to Good Health | Care Services |  | 1 | TSCC | Ongoing | 100%
| COMMUNITY | Care Services | Continued support of local voluntary |  |  | NHS
|  |  | groups such as hospital transport. |  |  | ABC
5.03 | A HEALTHIER | Access to Good Health | Care Services |  | 1 | TSCC | Ongoing | 100%
| COMMUNITY | Care Services | Maintain access to health care in |  |  | NHS
|  |  | Skipness. |  |  | ABC
6.01 | A COMPETITIVE, | Thriving Local Economy | Thriving Local Economy |  | 1 | TSCT | 1-2 yrs | 50% | 23/08/2018 Office in place and hoping to acquire
| EDUCATED AND |  | Cretae an enterprise centre with |  |  | THA |  |  | new premises in October 2018.
| WORKING |  | community access to Trust, assistance |  |  | TEC
| COMMUNITY |  | with an office, community hub,
development worker(s) and
administrator.
6.02 | A COMPETITIVE, | Thriving Local Economy | Thriving Local Economy |  | 1 | TSCT | 1-2 yrs | Not Started | 23/08/2018 Hoping to access by October 2018.
| EDUCATED AND |  | Plan use of Visit Scotland Office for |  |  | VS
| WORKING |  | commercial, heritage and visitor |  |  | TSCC
| COMMUNITY |  | services post 2019.
6.03 | A COMPETITIVE, | Thriving Local Economy | Thriving Local Economy |  | 2 | TSCC | 3 yrs | 20%
| EDUCATED AND |  | Establish a Chamber of Commerce.
WORKING
COMMUNITY
6.04 | A COMPETITIVE, | Thriving Local Economy | Thriving Local Economy |  | 2 | TALC | 1 yr and | 55% | 23/08/2018 Artmap, festivals, TALC digital arts, Feis,
| EDUCATED AND |  | More Arts Events. |  |  | TEC | ongoing |  | theatre groups and screen machine.
WORKING
COMMUNITY
6.05 | A COMPETITIVE, | Thriving Local Economy | Thriving Local Economy |  | 2 | TALC | 1 yr | 55%
| EDUCATED AND |  | Extended Artmap. |  |  | Artmap
WORKING
COMMUNITY
6.06 | A COMPETITIVE, | Thriving Local Economy | Thriving Local Economy |  | 1 | Tarbert Academy | 1-2 yrs | 15% | 23/08/2018 Feasibility study required to be carried
| EDUCATED AND |  | Assess transport needs. |  |  | Sports and arts |  |  | out.
| WORKING |  |  |  |  | groups
COMMUNITY
6.07 | A COMPETITIVE, | Thriving Local Economy | Thriving Local Economy |  | 1 | Tarbert Academy | 2 yrs | Not Started
| EDUCATED AND |  | Develop community transport |  |  | Sports and arts
| WORKING |  | initiative based on feasibility study. |  |  | groups
COMMUNITY
7.01 | A COMPETITIVE, | Business Development | Business Development |  | 4 | CC | Ongoing
| EDUCATED AND |  | Encourage and advise/assist |  |  | VS
| WORKING |  | accommodation providers to invest |  |  | HIE
| COMMUNITY |  | in improving current stock of holiday
accommodation.
7.02 | A COMPETITIVE, | Business Development | Business Development |  | 1 | TSCT | 1 yr | Not Started | 23/08/2018 Hoping to access by October 2018.
| EDUCATED AND |  | Acquire Visit Scotland office for
| WORKING |  | retail, visitor and heritage centre.
COMMUNITY
7.03 | A COMPETITIVE, | Business Development | Business Development |  | 2 | TSCT | 2 yrs | 25% | 23/08/2018 Moving onwards.
| EDUCATED AND |  | Develop Harbour Heritage project to |  |  | HIE
| WORKING |  | include heritage trail and archive of |  |  | Village groups
| COMMUNITY |  | Tarbert and Skipness community
albuym and other important artefacts.
7.04 | A COMPETITIVE, | Business Development | Business Development |  | 2 | THA | 2 yrs | 70% | 23/08/2018 Skipnees needs improving.
| EDUCATED AND |  | Continue to exploit advances in |  |  | HIE
| WORKING |  | technology to attract more 'remote |  |  | Broadband providers
| COMMUNITY |  | workers' and encourage home based
businesses.
7.05 | A COMPETITIVE, | Business Development | Business Development |  | 1 | THA | 3 yrs | 70% | Tarbert has improved but still problems in Skipness and Clachan.
| EDUCATED AND |  | Improve strength, quality and |  |  | HIE
| WORKING |  | reliability of broadbank and mobile |  |  | Broadband providers
| COMMUNITY |  | connections.
7.06 | A COMPETITIVE, | Business Development | Business Development |  | 4 | THA | 5 yrs
| EDUCATED AND |  | Develop boatyard facilities.
WORKING
COMMUNITY
7.07 | A COMPETITIVE, | Business Development | Business Development |  | 4 |  | - | N/A | 23/08/2018 Investigation complete, currently
| EDUCATED AND |  | Bunkhouse at Skipness as gateway to | [5 empty] | unfeasible.
| WORKING |  | Kintyre.
COMMUNITY
7.08 | A COMPETITIVE, | Business Development | Business Development |  | 1 | THA | 1 yr | Not Started
| EDUCATED AND |  | Using ABC Regeneration Fund, upgrade |  |  | ABC
| WORKING |  | Barmore Road junction.
COMMUNITY
7.09 | A COMPETITIVE, | Business Development | Business Development |  | 1 | THA | 2 yrs | 90% | 23/08/2018 Toilets and showers completed.
| EDUCATED AND |  | Improve on shore facilities and |  |  | ABC
| WORKING |  | parking.
COMMUNITY
7.10 | A COMPETITIVE, | Business Development | Business Development |  | 1 | ABC | 2 yrs | Not Started
| EDUCATED AND |  | Improve village parking.
WORKING
COMMUNITY
7.11 | A COMPETITIVE, | Business Development | Business Development |  | 1 | West Loch Shores | Achieved | 100%
| EDUCATED AND |  | Instigate and maintain camping/
| WORKING |  | motorhome park.
COMMUNITY
8.01 | A COMPETITIVE, | Achievement of | Achievement of Maximum Potential |  | 2 | TSCT, ABC, Landlords, | Ongoing | 35% | 23/08/2018 Consultation taking place.
| EDUCATED AND | Maximum Potential | Affordable family housing to |  |  | Highland Small
| WORKING |  | encourage new families and keep |  |  | Community
| COMMUNITY |  | existing families. |  |  | Housing Trust
TSCC
8.02 | A COMPETITIVE, | Achievement of | Achievement of Maximum Potential |  | 2 | TSCT | 1-5 yrs | 45%
| EDUCATED AND | Maximum Potential | Encourage local businesses to offer |  |  | TSCC
| WORKING |  | SVQ/apprenticeship training. |  |  | ABC
COMMUNITY
8.03 | A COMPETITIVE, | Achievement of | Achievement of Maximum Potential |  | 1 | TSCT | 1 yr | 20%
| EDUCATED AND | Maximum Potential | Ownership of community assets and |  |  | ABC
| WORKING |  | access to council facilities. |  |  | VS
COMMUNITY
8.04 | A COMPETITIVE, | Achievement of | Achievement of Maximum Potential |  | 1 | ABC | Ongoing | 55% | 23/08/2018 Assessment of housing need in progress.
| EDUCATED AND | Maximum Potential | Encourage new families to relocate to |  |  | TSCC
| WORKING |  | the area.
COMMUNITY
8.05 | A COMPETITIVE, | Achievement of | Achievement of Maximum Potential |  | 1 | TASC | Partially | 90% | 23/08/2018 Provision by Tarbert After School Care
| EDUCATED AND | Maximum Potential | Ensure adequate, affordable childcare |  |  | ABC | achieved |  | Tarbert Academy and doubling care after 2020.
| WORKING |  | facilities during work hours - with
| COMMUNITY |  | holiday cover.
8.06 | A COMPETITIVE, | Achievement of | Achievement of Maximum Potential |  | 2 | TSCT | Ongoing | 90%
| EDUCATED AND | Maximum Potential | Use every social enterprise project as
| WORKING |  | an opportunity for employment.
COMMUNITY
9.01 | A WELCOMING, | Sense of Place and Pride | Sense of Place and Pride |  | 2 | TSCT | Achieved | 90% | 23/08/2018 Community Benefit grants.
| VIBRANT AND |  | Focus on supporting and developing |  |  | TEC | and ongoing
| CONFIDENT |  | cornerstone events/festivals such as |  |  | THA
| COMMUNITY |  | the Scottish Series, Seafood/Music/ |  |  | TFC
Book and Christmas festivals,
Tarbert Fair, and Feis and the
facilities for them.
9.02 | A WELCOMING, | Sense of Place and Pride | Sense of Place and Pride |  | 2 | TSCT | Ongoing | 40% | 23/08/2018 Part of Heritage Centre project.
| VIBRANT AND |  | Maintain and update interpretitive |  |  | THA
| CONFIDENT |  | panels. |  |  | TSCC
COMMUNITY
9.03 | A WELCOMING, | Sense of Place and Pride | Sense of Place and Pride |  | 3 | TALC | Ongoing | 80%
| VIBRANT AND |  | Promote an ongoing programme of |  |  | TVH
| CONFIDENT |  | arts and leisure activities, learning
| COMMUNITY |  | opportunities and events at the
Templar Arts and Leisure Centre and
village halls.
9.04 | A WELCOMING, | Sense of Place and Pride | Sense of Place and Pride |  | 3 | TALC | Ongoing | 80%
| VIBRANT AND |  | Create avenues for local artists and |  |  | Hall Committee
| CONFIDENT |  | talent to showcase their work to the
| COMMUNITY |  | villages and the public.
9.05 | A WELCOMING, | Sense of Place and Pride | Sense of Place and Pride |  | 1 | All | From | 50%
| VIBRANT AND |  | Promote community and resident |  |  |  | January
| CONFIDENT |  | achievements publicly. |  |  |  | 2018
COMMUNITY
9.06 | A WELCOMING, | Sense of Place and Pride | Sense of Place and Pride |  | 1 | TSCT | Ongoing | 70%
| VIBRANT AND |  | Develop and implement business plan
| CONFIDENT |  | to follow closure of Visit Scotland
| COMMUNITY |  | office in 2019.
9.07 | A WELCOMING, | Sense of Place and Pride | Sense of Place and Pride |  | 1 | Tarbert Castle Trust | Achieved | 95%
| VIBRANT AND |  | Maintain Tarbert Castle Heritage Park, |  |  |  | and ongoing
| CONFIDENT |  | community orchard and woodland.
COMMUNITY
9.08 | A WELCOMING, | Sense of Place and Pride | Sense of Place and Pride |  | 1 | Tarbert Castle Trust | Achieved | 95%
| VIBRANT AND |  | Promote Tarbert Castle as a major |  |  |  | and ongoing
| CONFIDENT |  | visitor attraction.
COMMUNITY
9.09 | A WELCOMING, | Sense of Place and Pride | Sense of Place and Pride |  | 2 | Tarbert Castle Trust | 1 yr | 95%
| VIBRANT AND |  | Organise a community archaeological
| CONFIDENT |  | dig to further explor our castle ruins.
COMMUNITY
9.10 | A WELCOMING, | Sense of Place and Pride | Sense of Place and Pride |  | 2 | RNHT | 1 yr | 80% | 23/08/2018 Community Benefit grant.
| VIBRANT AND |  | Support Ring Net Heritage Trust and
| CONFIDENT |  | develop programme to develop their
| COMMUNITY |  | activities.
9.11 | A WELCOMING, | Sense of Place and Pride | Sense of Place and Pride |  | 1 | TSCT | 1-3 yrs | 65%
| VIBRANT AND |  | Improve and maintain existing |  |  | Paths for All
| CONFIDENT |  | footpath network. |  |  | ABC
| COMMUNITY |  |  |  |  | Tarbert Castle Trust
9.12 | A WELCOMING, | Sense of Place and Pride | Sense of Place and Pride |  | 2 | ABC | 1-2 yrs | 20%
| VIBRANT AND |  | Seasonal toilets, waiting room and |  |  | Cal Mac
| CONFIDENT |  | water at Claonaig. |  |  | TSCC
COMMUNITY
10.01 | A WELCOMING, | Safe and Attractive | A Safe and Attractive Place to Live, |  | 3 | TSCC | 2-3 yrs | Not Started
| VIBRANT AND | Place to Live, Work | Work and Visit |  |  | ABC
| CONFIDENT | and Visit | Review conservation status.
COMMUNITY
10.02 | A WELCOMING, | Safe and Attractive | A Safe and Attractive Place to Live, |  | 1 | TSCT | 1-2 yrs | 20% | 23/08/2018 Needs consultation which is currently
| VIBRANT AND | Place to Live, Work | Work and Visit |  |  | ACHA |  |  | taking place.
| CONFIDENT | and Visit | Develop mixed range of housing. |  |  | Fyne Homes
| COMMUNITY |  |  |  |  | Other Housing
Associations
10.03 | A WELCOMING, | Safe and Attractive | A Safe and Attractive Place to Live, |  | 1 | ABC |  | 100% | 23/08/2018 Housing needs assessment completed
| VIBRANT AND | Place to Live, Work | Work and Visit |  |  | Fyne Homes |  |  | April 2016.
| CONFIDENT | and Visit | Carry out housing needs assessment. |  |  | TSCC
COMMUNITY
10.04 | A WELCOMING, | Safe and Attractive | A Safe and Attractive Place to Live, |  | 1 | TSCT |  | 85% | 23/08/2018 Skipness school mothballed.
| VIBRANT AND | Place to Live, Work | Work and Visit |  |  | ABC
| CONFIDENT | and Visit | Maintain current area provisions with |  |  | NHS
| COMMUNITY |  | focus on Bank of Scotland, cashpoint, |  |  | Retail
post office, libraray, village halls,
health care services, Tarbert Academy
(primary and secondary education)
and Skipness Primary School.
10.05 | A WELCOMING, | Safe and Attractive | A Safe and Attractive Place to Live, |  | 2 | TSCC | 1 yr | Not Started
| VIBRANT AND | Place to Live, Work | Work and Visit |  |  | TS
| CONFIDENT | and Visit | Investigate the potential for improved |  |  | ABC
| COMMUNITY |  | traffic management such as 20 mph
zones, bypass of the trunk road,
designated car/lorry/coach parking
and pedestrian crossing.
10.06 | A WELCOMING, | Safe and Attractive | A Safe and Attractive Place to Live, |  | 3 | Schools | Achieved | 70%
| VIBRANT AND | Place to Live, Work | Work and Visit |  |  | TCT | and ongoing
| CONFIDENT | and Visit | Increase number and vairety of youth
| COMMUNITY |  | volunteering and involvement
opportunities.
10.07 | A WELCOMING, | Safe and Attractive | A Safe and Attractive Place to Live, |  | 2 | THA | 1-5 yrs | Not Started
| VIBRANT AND | Place to Live, Work | Work and Visit |  |  | ABC
| CONFIDENT | and Visit | Assess the implications of the threat |  |  | TSCC
| COMMUNITY |  | of tidal flooding to the area.
10.08 | A WELCOMING, | Safe and Attractive | A Safe and Attractive Place to Live, |  | 3 | TSCC | Ongoing | 70%
| VIBRANT AND | Place to Live, Work | Work and Visit |  |  | ABC
| CONFIDENT | and Visit | Support season roudn interest |  |  | THA
| COMMUNITY |  | through village.
10.09 | A WELCOMING, | Safe and Attractive | A Safe and Attractive Place to Live, |  | 1 | ABC Regneration | 1 yr | 30% | 23/08/2018 THA assessing parking need.
| VIBRANT AND | Place to Live, Work | Work and Visit |  |  | Project
| CONFIDENT | and Visit | Explore opportunities for more car |  |  | THA
| COMMUNITY |  | and coach parking.
10.10 | A WELCOMING, | Safe and Attractive | A Safe and Attractive Place to Live, |  | 2 | THA | 1 yr | Not Started | 23/08/2018 THA?
| VIBRANT AND | Place to Live, Work | Work and Visit |  |  | TSCT
| CONFIDENT | and Visit | Develop community owned filling
| COMMUNITY |  | station.
11.01 | A WELCOMING, | Capacity | Capacity |  | 1 | TSCT |  | 50%
| VIBRANT AND |  | Recruit a professional to oversee
| CONFIDENT |  | implementation of Community Plan,
| COMMUNITY |  | broker relationships between groups
and give advice when needed.
11.02 | A WELCOMING, | Capacity | Capacity |  | 2 | TSCC | ongoing | 60%
| VIBRANT AND |  | Support a mechanism for publicly |  |  | TSCT
| CONFIDENT |  | recognising the efforts and
| COMMUNITY |  | achievement made by individuals,
volunteers and groups.
11.03 | A WELCOMING, | Capacity | Capacity |  | 3 | TSCT | 1 yr | 80%
| VIBRANT AND |  | Design, implement and maintain a
| CONFIDENT |  | community asset management plan.
COMMUNITY
12.01 | A WELCOMING, | Good Visitor Experience | Good Visitor Experience |  | 1 | VS until 2019 then | 1-2 yrs | Not Started | 23/08/2018 New venture to be undertaken through
| VIBRANT AND |  | Make readily available essential |  |  | new company |  |  | TSCT to provide a village hub and heritage centre
| CONFIDENT |  | visitor information regarding | [5 empty] | from October 2018.
| COMMUNITY |  | accommodation, catering and events/
activities using a central website, the
Tourist Information Centre and
regular newsletters.
12.02 | A WELCOMING, | Good Visitor Experience | Good Visitor Experience |  | 3 | Retail | 2 yrs | Not Started
| VIBRANT AND |  | Encourage local businesses to
| CONFIDENT |  | cross-promote other local services,
| COMMUNITY |  | facilities, events and amenities.
12.03 | A WELCOMING, | Good Visitor Experience | Good Visitor Experience |  | 3 | THA | 2 yrs | 50%
| VIBRANT AND |  | Consolidate and update signage both |  |  | TSCT
| CONFIDENT |  | inside and outside the area. |  |  | ABC
COMMUNITY
12.04 | A WELCOMING, | Good Visitor Experience | Good Visitor Experience |  | 4 | TSCT | 4 yrs | Not Started | 23/08/2018 New venture to be undertaken through
| VIBRANT AND |  | Digitally archive old photographs of |  |  | THA |  |  | TSCT to provide a village hub and heritage centre
| CONFIDENT |  | Tarbert and Skipness. |  |  | Heritage Group |  |  | October 2018.
COMMUNITY
12.05 | A WELCOMING, | Good Visitor Experience | Good Visitor Experience |  | 3 | TSCT | Achieved | 100%
| VIBRANT AND |  | Repair path to White Shore. |  |  |  | and ongoing
CONFIDENT
COMMUNITY
13.01 | AN INCLUSIVE, | Access for All | Access For All |  | 3 | TSCC | 5yrs to make | Not Started | 23/08/2018 Sustrans currently looking at a 2-3 year
| FAIR AND CARING | and | Increase amount of all abilities' |  |  | ABC | significant |  | lead in time for a cycle/pedestrian route from Tarbert
| COMMUNITY | Opportunities to Affect | access to walks and A83 pavements. |  |  | TS | increase |  | to Kennacraig.
Positive Change
13.02 | AN INCLUSIVE, | Access for All | Opportunities to Affect Positive |  | 1 | TSCT | Achieved | 100%
| FAIR AND CARING | and | Change
| COMMUNITY | Opportunities to Affect | Develop criteria for disbursement of
|  | Positive Change | Community Plan.
13.03 | AN INCLUSIVE, | Access for All | Opportunities to Affect Positive |  | 1 | TSCT | Achieved | 100%
| FAIR AND CARING | and | Change |  |  | TSR
| COMMUNITY | Opportunities to Affect | Create company able to invest in
|  | Positive Change | community renewables.
13.04 | AN INCLUSIVE, | Access for All | Opportunities to Affect Positive |  | 4 | TSCT | - | N/A | 23/08/2018 Community fuel buying and community
| FAIR AND CARING | and | Change | [5 empty] | wodoland unfeasible at present.
| COMMUNITY | Opportunities to Affect | Community fuel project to address
|  | Positive Change | local fuel prices and fuel poverty:
* Communual fuel buying
* Investigate renewables
* Community woodland
13.05 | AN INCLUSIVE, | Access for All | Opportunities to Affect Positive |  | 1 | CC | Annually | 100%
| FAIR AND CARING | and | Change |  |  | TSCC
| COMMUNITY | Opportunities to Affect | Rolling or annual review of T&S |  |  | TSCT
|  | Positive Change | Community Plan accessible to all |  |  | TEC
online - The 'Living Plan'.
13.06 | AN INCLUSIVE, | Access for All | Opportunities to Affect Positive |  | 4 | TSCC | 1 yr | 50% | 23/08/2018 RNLI carrying out review of provision.
| FAIR AND CARING | and | Change |  |  | THA
| COMMUNITY | Opportunities to Affect | Investigateneed for Lifeboat/Rescue |  |  | RNLI
|  | Positive Change | Boat.
13.07 | AN INCLUSIVE, | Access for All | Opportunities to Affect Positive |  | 1 | ABC | 6 mths | Not Started
| FAIR AND CARING | and | Change |  |  | TSCC
| COMMUNITY | Opportunities to Affect | Community resilience plans for
|  | Positive Change | Tarbert and Skipness.
13.08 | AN INCLUSIVE, | Access for All | Social Inclusion |  | 3 | TSCT | Ongoing | 30% | 23/08/2018 Need housing and opportunities for
| FAIR AND CARING | and | Create opportunities for young people |  |  | ABC |  |  | employment.
| COMMUNITY | Opportunities to Affect | to remain and work in the area. |  |  | TSCC
Positive Change
13.09 | AN INCLUSIVE, | Access for All | Social Inclusion |  | 3 | TSCC | 5-6 yrs | Not Started
| FAIR AND CARING | and | Improve public transport connections |  |  | ABC
| COMMUNITY | Opportunities to Affect | between local communities.
Positive Change
13.10 | AN INCLUSIVE, | Access for All | Social Inclusion |  | 3 |  | 6 mths | Not Started
| FAIR AND CARING | and | Evaluate disabled access to Tarbert
| COMMUNITY | Opportunities to Affect | and Skipness war memorials.
Positive Change
13.11 | AN INCLUSIVE, | Access for All | Social Inclusion Develop befriending for vulnerable adults and continue befriending for vulnerable children. |  | 3 | Dochas Centre | 1-2 yrs | 85%
| FAIR AND CARING | and | Develop befriending for vulnerable |  |  | Befrienders
| COMMUNITY | Opportunities to Affect | adults and continue befriending for |  |  | NHS
|  | Positive Change | vulnerable children. |  |  | ABC
13.12 | AN INCLUSIVE, | Access for All | Social Inclusion |  | 1 | Dochas Centre | 1-2 yrs | 50%
| FAIR AND CARING | and | Develop friendship network for frail |  |  | Befrienders
| COMMUNITY | Opportunities to Affect | elderly in Skipness. |  |  | NHS
|  | Positive Change |  |  |  | ABC
13.13 | AN INCLUSIVE, | Access for All | Social Inclusion |  | 3 | ABC | 5 yrs | Not Started
| FAIR AND CARING | and | Improve local walks (or parts thereof)
| COMMUNITY | Opportunities to Affect | to 'All Ability' standards.
Positive Change
14.01 | A GREENER AND | Self-Sustaining and | Self-Sustaining and Adequate Provision |  | 3 | Retailers | Achieved | 35%
| SUSTAINABLE | Adequate Provision | Promote the use of local produce and |  |  | Producers | partially
| COMMUNITY |  | seafood. |  |  |  | through
local
produce
14.02 | A GREENER AND | Self-Sustaining and | Self-Sustaining and Adequate Provision |  | 1 | TSCT | Within | 40% | Housing needs assessment taking place 2018.
| SUSTAINABLE | Adequate Provision | Work with housing associations to |  |  | Highland Small | 2 yrs
| COMMUNITY |  | resolve lack of 3-4 bedroom houses |  |  | Community
|  |  | in Tarbert. |  |  | Housing Trust
14.03 | A GREENER AND | Self-Sustaining and | Self-Sustaining and Adequate Provision |  | 3 | Retailers | Ongoing | 60%
| SUSTAINABLE | Adequate Provision | Work with local suppliers to develop |  |  | Producers
| COMMUNITY |  | wood fuel sources to encourage more
use of wood fuel.
14.04 | A GREENER AND | Self-Sustaining and | Self-Sustaining and Adequate Provision |  | 2 | Scottish Water | 1 yr | Not Started
| SUSTAINABLE | Adequate Provision | Resolve water quality and supply |  |  | Windfarm company
| COMMUNITY |  | issues to Skipness and Claonaig.
14.05 | A GREENER AND | Self-Sustaining and | Self-Sustaining and Adequate Provision |  | 3 | Alienergy | 2 yrs | 50%
| SUSTAINABLE | Adequate Provision | Educate community to use power
| COMMUNITY |  | responsibly.
14.06 | A GREENER AND | Self-Sustaining and | Self-Sustaining and Adequate Provision |  | 1 | TSCC | 6 mths | Not Started
| SUSTAINABLE | Adequate Provision | Prepare proposals to achieve |  |  | ABC
| COMMUNITY |  | resilience within the community.
15.01 | A GREENER AND | Natural and Built | Natural and Built Environment |  | 2 | TSCT | Achieved | 100%
| SUSTAINABLE | Environment | Reinstate community cleaning of |  |  | TLFYC | Annually
| COMMUNITY |  | beaches. |  |  | THA
15.02 | A GREENER AND | Natural and Built | Natural and Built Environment |  | 4 | Schools | Partially | 80%
| SUSTAINABLE | Environment | Gardening project for young people. |  |  | TSCT | achieved
COMMUNITY
15.03 | A GREENER AND | Natural and Built | Natural and Built Environment |  | 2 | TSCT | Partially | 80%
| SUSTAINABLE | Environment | Improve footpaths. |  |  | Local groups | Achieved
| COMMUNITY |  |  |  |  | ABC | and ongoing
15.04 | A GREENER AND | Natural and Built | Natural and Built Environment |  | 1 | TSCT | 1 yr | Not Started
| SUSTAINABLE | Environment | Reduce plastic use. |  |  | Local groups
| COMMUNITY |  |  |  |  | Tarbert Academy