## 26.06.2019
Community Action Plan 2016-21
Updated : June 2019
No. of Actions
| 1 - 39% | 3
| 40 - 69% | 8
| 70 - 99% | 6
| 100% | 16
| Not Started | 6
| Blank | 12
Action |  |  | Priority | By Whom | Timescale | % Complete | Comments
Housing
| Tackle dampness and poor insulation of housing. |  | 2 | Alienergy, ACHA, Fyne Homes | Ongoing
1.02 | Affordable family housing to encourage new families and keep existing families. |  | 2 | TSCT, ABC, Landlords, TSCC, Highlands Small Communities Housing Trust | Ongoing | 40% | Options appraisal currently taking place.
1.03 | Develop a mixed range of housing, including affordable housing to encourage new families to relocate and keep existing families. |  | 1 | TSCT, Housing Associations | 1-2 yrs | 20% | Options appraisal currently taking place.
1.04 | Carry out housing needs assessment. |  | 1 | ABC, Fyne Homes, TSCC |  | 100% | Housing needs assessments completed April 2016 and September 2018.
1.05 | Work with housing associations to resolve lack of 3-4 bedroom houses in Tarbert. |  | 1 | TSCT, Highland Small Communities Housing Trust, Housing Associations | Within 2 yrs | 20% | Housing needs assessments completed April 2016 and September 2018.
Business Development
2.01 | Develop and implement business plan to follow closure of Visit Scotland office in 2018. |  | 1 | TSCT | Ongoing | 20%
2.02 | Create an enterprise centre with community access to Trust assistance with an office, community hub, development workers and administrator. |  | 1 | TSCT | 1-2 yrs | 80% | Office and staff in place.
2.03 | Plan use of Visit Scotland Office for heritage, visitor and Trust hub services post 2018. |  | 1 | TSCT, VS, TSCC | 1-2 yrs | 80% | Access achieved November 2018 and heritage display opened June 2019.
2.05 | Establish a Chamber of Commerce. |  | 2 | TSCC | 3 yrs | Not Started
2.06 | Continue to exploit advances in technology to attract more 'remote workers' and encourage home based businesses. |  | 2 | THA, HIE, TSCC, broadband providers | 2 yrs | 50% | Skipness needs improvement.
2.07 | Improve strength, quality and reliability of broadband and mobile connections. |  | 1 | THA, HIE, TSCC, broadband providers | 1 yr | 50% | Tarbert has improved but still problems in Skipness and Clachan.
2.08 | Improve on shore facilities and parking. |  | 1 | THA, ABC | 2 yrs | 80% | Toilets, showers and harbour office completed. Parking still to be addressed.
2.09 | Encourage local businesses to offer SVQ/apprenticeship training. |  | 2 | TSCT, TSCC, ABC | 1-5 yrs
2.10 | Ensure adequate, affordable childcare facilities during working hours - with holiday cover. |  | 1 | TASC, ABC | Achieved | 100% | Provision by Tarbert After School Care and Tarbert Academy doubling care after 2020.
2.11 | Maintain current area provisions with focus on Bank of Scotland cashpoint, post office, libraray, village halls, health care services, Tarbert Academy (primary and secondary education. |  | 1 | TSCT, ABC, NHS, Retail |  | 90% | Skipness school mothballed.
2.12 | Support season round interest through village. |  | 3 | TSCC, ABC, THA, Tarbert Life | Ongoing
Action |  |  | Priority | By Whom | Timescale | % Complete | Comments
Social Involvement
3.01 | Promote local community groups' activities, events and achievements as well as provide information on how to get involved via diary. |  | 3 | All | Ongoing | 100% | Events promoted through social media, Tarbert Life and local advertising.
3.02 | Campaign to recruit new Trust membership. |  | 2 | TSCT | 1 yr | 60% | TSCT membership up 10% and corporate membership also promoted.
3.03 | Support existing community places to maintain and improve facilities. |  | 2 | TSCT, TVH, TALC, THA | Ongoing | 100% | Community Benefit Fund and access to Community Trust.
3.04 | Continued support of local voluntary groups such as hospital transport, wellbeing group and befriending in all communities. |  | 1 | TSCC, NHS, ABC, Dochas Centre, Befrienders | Ongoing | 60% | Community Benefit Fund and access to Community Trust.
3.05 | Promote an ongoing programme of arts and leisure activities, learning opportunities and events at the Templar Arts and Leisure Centre and village halls. |  | 3 | TALC, TVH, Others | Ongoing | 100%
3.06 | Increase number and variety of youth volunteering and involvement opportunities. |  | 3 | Schools, TSCT | Achieved and ongoing | 100%
3.07 | Develop criteria for disbursement of Community Benefit. |  | 1 | TSCT | Achieved | 100%
Paths
4.01 | New path to Kennacraig to complete circular walk from village centre via West Loch and Corranbuie track. |  | 1 | TSCC, Bear Scotland, West Loch Shores, Sustrans | 6-12 mths |  | Argyll and Bute Council highlighted this section and Sustrans in 2018 as top priority of the new for improvement in Argyll and Bute.
4.02 | Improve and maintain existing footpath network. |  | 1 | TSCT, Paths for All, ABC | 1 yr | 80% | White Shore path has been upgraded. Castle paths have been completed. Investigate footpath to Stonefield.
4.03 | Increase all ability section in walks. |  | 4 | TSCC |  | 50%
4.04 | Support groups with funding, governance and safeguarding. |  | 1 | TSCT | Ongoing | 100% | Community Benefit procedures in place and 2017-18 grants dispersed. Access to Community Trust.
Healthy Living and Health Services
5.01 | Promote the use of fresh foods and healthy diets. |  | 3 | NHS, Retailers | Ongoing | 100% | Work through school with food bank to create recipe cards. After School Care cooking lessons with children. Promotion of local produce.
5.02 | Investigate water quality and supply issues to Skipness and Claonaig. |  | 2 | Scottish Water | 2 yrs
5.03 | Maintain current health services in Tarbert and Skipness. |  | 1 | NHS | Ongoing |  | Maintain health centre, opticians, dentist and mobile surgeries.
Action |  |  | Priority | By Whom | Timescale | % Complete | Comments
Visitor Experience
6.01 | More arts events and extended Art Map. |  | 2 | TALC, TEC, TVH, Artmap | 1 yr and ongoing | 100% | Artmap, festivals, TALC digital arts, Feis, theatre groups and screen machine.
6.02 | Encourage and advise/assist accommodation providers to invest in improving current stock of holiday accommodation. |  | 4 | TSCC, HIE | Ongoing
6.03 | Improve village parking. |  | 1 | ABC, TSCC, THA | 2 yrs | Not Started | New parking places to be created after Barmore Road junction improved.
6.04 | Develop camping/motorhome park. |  | 1 | West Loch Shores | Complete | 100%
6.05 | Focus on supporting and developing cornerstone events/festivals such as the Scottish Series, Seafood/Music/Book, Viking and Christimas festivals, Tarbert Fair, and Feis and the facilities for them. |  | 2 | TSCT, TEC, TFC, ABC | Achieved and ongoing | 100% | Community Benefit grants and local fund raising.
6.06 | Maintain and update interpretitive panels. |  | 2 | TSCT, THA, TSCC | Ongoing |  | Part of Tarbert Life - due 2020.
6.07 | Seasonal toilets, waiting room and water at Claonaig. |  | 2 | ABC, Cal Mac, TSCC | 1-2 yrs | Not Started
6.08 | Improve and update signage. |  | 1 | THA, TSCT, ABC, TSCC | 1 yr |  | Highlighted in local walking and cycling consultation.
6.09 | Develop heritage project to include heritage trail and archive of Tarbert and Skipness community database and other important artefacts. |  | 2 | TSCT, HIE, village groups, Tarbert Life | 2 yrs | 80% | Heritage project opened June 2019.
Heritage
7.01 | Maintain Tarbert Castle Heritage Park, community orchard and woodland. |  | 1 | Tarbert Castle Trust | Achieved and ongoing | 100%
7.02 | Promote Tarbert Castle as a major visitor attraction. |  | 1 | Tarbert Castle Trust | Achieved and ongoing | 100%
7.03 | Organise a community archaeological dig to further explore our castle ruins. |  | 2 | Tarbert Castle Trust | Achieved | 100%
7.04 | Support Ring Net Heritage Trust and develop programme to promote their facilities. |  | 2 | RNHT | 1 yr | 60%
Transport
8.01 | Assess transport need and develop community transport initiative. |  | 1 | Tarbert Academy, sports and arts groups | 1 yr | Not Started | Feasibility study required to be carried out.
8.02 | Using ABC Regeneration Fund, upgrade Barmore Road junction. |  | 1 | THA, ABC | 1 yr |  | Planned Autumn 2019.
8.03 | Investigate the potential for improved traffic management such as 20mph zones, bypass of the trunk road, designated car/lorry/coach parking and pedestrian crossing. |  | 2 | TSCC, Bear Scotland, ABC | 1 yr | Not Started
Action |  |  | Priority | By Whom | Timescale | % Complete | Comments
Greener Community
9.01 | Educate community to use power responsibly. |  | 3 | Alienergy | 2 yrs
9.02 | Prepare proposals to achieve resilience within the community. |  | 1 | TSCC, ABC | 6 mths | Not Started
9.03 | Reinstate community cleaning of beaches. |  | 2 | TSCT, TLFYC, THA | Achieved annually | 100% | In 2019, beach clean carried out over two days.
9.04 | Reduce plastic use. |  | 1 | TSCT, Tarbert Academy, local groups | Ongoing
9.05 | Identify areas within villages that need clearing and cleaning. |  | 2 | TSCT, TSCC, Tarbert Academy, ABC | Achieved and ongoing | 50%
Glossary
ABC | Argyll and Bute Council
ACHA | Argyll Community Housing Association
HIE | Highlands and Islands Enterprise
RNHT | Ring Net Heritage Trust
TALC | Templar Arts and Leisure Centre
TASC | Tarbert After School Care
TEC | Tarbert Enterprise Company
TFC | Tarbert Festivals Committee
THA | Tabert Harbour Authority
TLFYC | Tarbert Loch Fyne Yacht Club
TSCC | Tarbert and Skipness Community Council
TSCT | Tarbert and Skipness Community Trust
TVH | Tarbert Village Hall
VS | Visit Scotland until 2019
Background
In 2009, Tarbert and Skipness Community Trust (TSCT) commissioned Jura Consultants to produce a community plan for Tarbert. At the time, the community in Skipness did not want to engage with the process so the report was for Tarbert alone. This was completed in March 2010 after extensive consultations with local community groups, businesses and individuals.
The aims of the plan are to create:
* A healthier community
* A competitive, educated and working comunity
* A welcoming, vibrant and confident community
* An inclusive, fair and caring community
* A greener andd sustainable community
Subsequently, the plan has been important in assisting developments by demonstrating to potential funders that this community works in a planned, consistent and responsible way. As a result, the years 2010 to 2019 have seen development in our communities.
The community in Skipness agreed to the plan in principle in 2014 and wish to be included in any updates of it.
In 2014, the Trust came to the conclusion that it needed to develop the plan for the next 5 years to make it more accessible and ensure that local residents, community organisations and businesses have the opportunity to contribute to it. Thus, the Trust has:
* Reviewed the 2010 plan.
* Instigated, in 2014, an annual Community Consultation Event in order to:
▫ listen to the community's concerns, ideas and priorties.
▫ amend the action plan accordingly.
* Started work to make it a 'Living Plan', available online and accessible to all by April 2016.
As a result of the three develoment days, and the review of the 2010 plan in August 2015, the Trust is now able to progress a new action plan to meet the challenges for the next 5 years, until 2024, to become the basis for the 'Living Plan', updating annually.